## 2024-2027
Agriculture and Rural Development 2021-2027 Strategy of Georgia Action Plan for 2024-2027
GOAL 1: |  | Competitive agricultural and non-agricultural sectors |  |  |  |  | Link to SDGs: |  | 2; 4; 5; 8; 9
IMPACT Indicator 1.1: |  | Output of primary agricultural products and food products made by processing agricultural products |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm | Final
|  |  |  | Year | 2023 | 2025 | 2027 |  | GEOSTAT Website www.geostat.ge
|  |  |  | Value | GEL 16.6 Billion | GEL 19.5 Billion | GEL 24 Billion
OBJECTIVE 1.1: |  | To raise awareness/knowledge of farmers and entrepreneurs
OUTCOME INDICATOR 1.1.1: |  | Employment indicators of graduates from vocational educational programs in agriculture and the environment, within their respective professions. |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Alumni survey, The Skills Agency
|  |  |  | Value | 44% | 46% |  | 55%
Risk: |  | Delayed economic growth in the country.
# | Activity | # | Output Indicator | Source of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
1.1.1.1 | Provision of effective extension services to farmers | 1.1.1.1.1 | Extension services will be provided to 140,500 beneficiaries (individuals and legal entities) | MEPA Annual Report | The Ministry of Environmental Protection and Agriculture of Georgia / Rural Development Agency, NCLE |  | 2027,IV |  | Administrative costs
1.1.1.2 | Design professional qualifications in cooperation with the private sector | 1.1.1.2.1 | Professional standards developed in accordance with the sectoral map | Approved professional standards | The Ministry of Education, Science and Youth of Georgia / Skills Agency | The Ministry of Environmental Protection and Agriculture of Georgia | 2025,IV | 5978240 | 5978240 | 32 03 02 |  |  |  | 1989120 | 1989120 | 1000000 | 1000000
|  | 1.1.1.2.2 | Vocational education standards developed in accordance with the sectoral map | Approved vocational education standards | The Ministry of Education, Science and Youth of Georgia / Skills Agency | The Ministry of Environmental Protection and Agriculture of Georgia | 2025, IV
1.1.1.3 | Increase availability of vocational programs in agriculture and environment | 1.1.1.3.1 | The number of individuals enrolled in vocational programs in agriculture and environment increased by 10% | Education Management Information System (EMIS) data | The Ministry of Education, Science and Youth of Georgia |  | 2027,IV | 14550000 | 14550000 | 32 03 01 |  |  |  | 3500000 | 3500000 | 3600000 | 3950000
1.1.1.4 | Further development of the vocational training and professional retraining program in agriculture and environment | 1.1.1.4.1 | The number of participants in agriculture and environmental vocational training and professional retraining programs increased by 10% | Education Management Information System (EMIS) data | The Ministry of Education, Science and Youth of Georgia / Skills Agency |  | 2026,IV | 960000 | 960000 | 32 03 02 |  |  |  | 315000 | 320000 | 325000 | 0
|  | 1.1.1.4.2 | Vocational training and professional retraining programs in agriculture and environment are available in all regions of Georgia | Education Management Information System (EMIS) data | The Ministry of Education, Science and Youth of Georgia / Skills Agency |  | 2025,IV
1.1.1.5 | Facilitate private sector's contribution to promote development of skills in agriculture and environment | 1.1.1.5.1 | Sectoral networks of vocational education teachers in agricultural programs bolstered with the private sector support | Report of the Skills Agency | The Ministry of Education, Science and Youth of Georgia / Skills Agency |  | 2024,IV | 213000 | 213000 | 32 03 02 |  |  |  | 213000
|  | 1.1.1.5.2 | The number of agricultural and environmental work-based training programs increased by 50% | Education Management Information System (EMIS) data | The Ministry of Education, Science and Youth of Georgia / Skills Agency | UNDP | 2027,IV
1.1.1.6 | Support the promotion of agriculture and environment professions | 1.1.1.6.1 | Awareness-raising campaigns conducted with the involvement of the private sector to promote agricultural and environmental vocations | Report of the Skills Agency | The Ministry of Education, Science and Youth of Georgia / Skills Agency |  | 2027,IV | 1346000 | 1346000 | 32 03 02 |  |  |  | 296000 | 300000 | 350000 | 400000
1.1.1.7 | Enhance availability and access to vocational education programs | 1.1.1.7.1 | Vocational education institutions available additionally in at least 2 municipalities | Report of the Ministry of Education, Science and Youth of Georgia | The Ministry of Education, Science and Youth of Georgia | Education and Science Infrastructure Development Agency, LEPL / National Center for Education Quality Enhancement, LEPL | 2026,IV | 5748830 | 5748830 | 32 07 02 |  |  |  | 5748830
|  | 1.1.1.7.2 | Vocational programs are available in 30 public schools | EMIS data | The Ministry of Education, Science and Youth of Georgia / Skills Agency | ADB/UNDP | 2027,IV | 16000000 | 16000000 | 32 10 |  |  |  | 8000000 | 6000000 | 2000000 | 0
OBJECTIVE 1.2: |  | To develop agricultural and non-agricultural value chain by focusing on diversification, innovative technologies, cooperation, and support to producers' unions; To increase access to various financial instruments
OUTCOME INDICATOR 1.2.1: |  | The number of unique beneficiaries who have made investments in the agri-food sector |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Rural Development Agency, NCLE Report
|  |  |  | Value | 50 630 | 59 000 |  | 68 000
Risk: |  | Low activity among potential beneficiaries, potential shortage of funds; difficult to forecast new demands in the long run, considering the changes in the economic situation in the agricultural sector
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
1.2.1.1 | Co-funding of interest rate on agro credits (Preferential agro-credit project) | 1.2.1.1.1 | Interest rates for134,000 preferential agricultural loans/leases were co-funded | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 770000000 | 770000000 | 31 05 02 01 |  |  |  | 200000000 | 190000000 | 190000000 | 190000000
1.2.1.2 | Subsidizing insurance premium for the development of agro insurance (The agro insurance program) | 1.2.1.2.1 | 86,200 ha land area insured | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 63000000 | 63000000 | 31 05 03 |  |  |  | 12000000 | 17000000 | 17000000 | 17000000
1.2.1.3 | Development/contracting of modern orchards (the program Plant the Future) | 1.2.1.3.1 | 7,500 ha new perennial orchards developed/contracted and the appropriate infrastructure organized | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 124800000 | 124800000 | 31 05 04 |  |  |  | 26000000 | 23600000 | 38100000 | 37100000
1.2.1.4 | Rehabilitation of the Georgian tea plantations (The program for the rehabilitation of Georgian tea plantations) | 1.2.1.4.1 | 390 ha tea plantations rehabilitated | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2026, IV | 1500000 | 1500000 | 31 05 05 |  |  |  | 500000 | 500000 | 500000 | 0
1.2.1.5 | Co-financing processing and storage enterprises | 1.2.1.5.1 | The creation of 248 processing enterprises and/or storage infrastructure was fully or partially financed | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 105000000 | 105000000 | 31 05 06 |  |  |  | 17000000 | 25000000 | 31000000 | 32000000
1.2.1.6 | Equip cooperatives with storage and processing equipment to develop infrastructure and facilities of agricultural cooperatives | 1.2.1.6.1 | 31 agricultural cooperatives received funding for organizing storage/warehousing and processing infrastructure | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 18000000 | 18000000 | 31 05 09 |  |  |  | 3000000 | 5000000 | 5000000 | 5000000
1.2.1.7 | Co-financing the acquisition of agricultural equipment | 1.2.1.7.1 | Co-financing will be provided to 650 beneficiaries for the purchase of agricultural (including harvesting) equipment (2024-2027) 3,500 rotary cultivators will be financed in 2024 | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 68000000 | 68000000 | 31 05 10 |  |  |  | 20000000 | 16000000 | 16000000 | 16000000
1.2.1.8 | Co-financing of enterprises to establish a competitive, diversified and sustainable dairy sector (The Dairy Modernization and Market Access (DIMMA)) | 1.2.1.8.1 | 130 beneficiaries received co-financing | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE | International Fund for Agricultural Development | 2024, IV | 5000000 | 5000000 | 31 05 15 01 02 |  |  |  | 5000000 |  |  | 0
1.2.1.9 | Co-finance the establishment of greenhouses for economically inactive women in order to integrate them into agricultural activities (A pilot program specifically designed for women) | 1.2.1.9.1 | Contracts will be made with 45 beneficiary women for co-financing the development of greenhouse farms | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 2500000 | 2500000 | 31 05 14 |  |  |  | 1000000 | 500000 | 500000 | 500000
1.2.1.10 | Co-financing existing as well as startup small and medium sized businesses in the regions, with the involvement of local action groups | 1.2.1.10.1 | 80 beneficiaries received co-financing from the RDA | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 6000000 | 6000000 | 31 05 17 |  |  |  | 1000000 | 1000000 | 2000000 | 2000000
1.2.1.11 | Subsidize the cost of the products for the production of hazelnuts for hazelnut orchard owners/holders | 1.2.1.11.1 | 120,000 beneficiaries received subsidies within the frame of the Program | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2025, IV | 40000000 | 40000000 | 31 05 18 |  |  |  | 20000000 | 20000000 |  | 0
1.2.1.12 | Co-finance the purchase of agricultural mechanization and implements for cooperatives | 1.2.1.12.1 | Co-financing of the acquisition of agricultural equipment and implements was provided for 130 beneficiaries | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 8000000 | 8000000 | 31 05 16 |  |  |  | 2000000 | 2000000 | 2000000 | 2000000
1.2.1.13 | Install meteorological stations to gather information for analysis to inform consultations about climate and pests/diseases-related risks during agricultural activities | 1.2.1.13.1 | 11 meteorological stations rehabilitated/installed in two pilot regions (Shida Kartli, Kakheti) | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE | UNDP, National Food Agency, LEPL, Scientific-Research Center of Agriculture, LEPL, National Environmental Agency, LEPL | 2025, I | 411087 |  |  | 411087 | UNDP |  | 350198 | 60889
1.2.1.14 | Support the increase of bio/organic production | 1.2.1.14.1 | Contracts will be made/co-financing will be provided to 420 beneficiaries | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 5500000 | 5500000 | 31 05 13 |  |  |  | 1000000 | 1000000 | 1500000 | 2000000
1.2.1.15 | Implement the Innovations Grants program for the regions (Around GEL 25,000) | 1.2.1.15.1 | 40 startups financed in 10 regions of Georgia | Report of the Georgia's Innovation and Technologies Agency, LEPL | The Ministry of Economy and Sustainable Development of Georgia / Report of the Georgia's Innovation and Technologies Agency, LEPL |  | 2024 | 1000000 | 600000 | 24 08 02 |  |  | 400000 | 1,000,000 (Including gap - GEL 400,000)
1.2.1.16 | Co-finance the interest on credit and an object of the leasing in industries | 1.2.1.16.1 | Each year, interests for 300 loans/leases are co-financed for the expansion/upgrading/modernization of new or existing enterprises | Annual Report of Enterprise Georgia, LEPL | The Ministry of Economy and Sustainable Development of Georgia / Enterprise Georgia, LEPL |  | 2027 | 30500000 | 30500000 | 24 07 02 01 |  |  |  | 12000000 | 6500000 | 6000000 | 6000000
1.2.1.17 | Co-finance the interest on credit and the object of the lease for the development/expansion of the hotel industry | 1.2.1.17.1 | Each year, interest for 100 loans/leases are co-financed for the expansion/upgrading/modernization of new or existing hotels | Annual Report of Enterprise Georgia, LEPL | The Ministry of Economy and Sustainable Development of Georgia / Enterprise Georgia, LEPL |  | 2027 | 16000000 | 16000000 | 24 07 02 01 |  |  |  | 8000000 | 3000000 | 2500000 | 2500000
1.2.1.18 | Co-finance the participation of companies in international exhibitions to support exports | 1.2.1.18.1 | Annually, 50 instances of co-financing of agro food producing companies for various international exhibitions and relevant priority markets | Annual Report of Enterprise Georgia, LEPL | The Ministry of Economy and Sustainable Development of Georgia / Enterprise Georgia, LEPL | USAID Agriculture Program | 2027 | 12000000 | 12000000 | 24 07 02 01 |  |  |  | 3000000 | 3000000 | 3000000 | 3000000
1.2.1.19 | Establish an integrated database for the land fund and develop a land balance | 1.2.1.19.1 | Decrypted data from the integrated database for the land fund and published land balance | Report of the National Agency for Sustainable Land Management and Land Use Monitoring, LEPL | The Ministry of Environmental Protection and Agriculture / The National Agency for Sustainable Land Management and Land Use Monitoring, LEPL | _ | 2024,IV |  | Administrative costs
1.2.1.20 | Develop legislation on the management of pastures | 1.2.1.20.1 | The Georgian Law on the Management of Pastures drafted | Annual report of the Ministry of Environmental Protection and Agriculture | The Ministry of Environmental Protection and Agriculture/ Department of Hydro-Melioration and Land Management |  | 2025, IV | 25000 |  |  | 25000 | GEF |  | 25000
1.2.1.21 | Implement the state program for availability of state-owned pastures | 1.2.1.21.1 | Around 10,000 ha land plots for pasture available for leasing | Report of the National Agency for Sustainable Land Management and Land Use Monitoring, LEPL | The Ministry of Environmental Protection and Agriculture / The National Agency for Sustainable Land Management and Land Use Monitoring, LEPL | The Ministry of Economy and Sustainable Development / National Agency of State Property, LEPL | 2025, IV |  | Administrative costs
1.2.1.22 | Inventory of wind protection belts | 1.2.1.22.1 | About 13,900 ha inventoried wind protection belts | Report of the National Agency for Sustainable Land Management and Land Use Monitoring, LEPL | The Ministry of Environmental Protection and Agriculture / The National Agency for Sustainable Land Management and Land Use Monitoring, LEPL | _ | 2026,IV | 6960000 | 5500000 | 31 15 02 |  |  | 1460000 | 1500000 | 2,800,000 (including gap - GEL 800,000) | 2,660,000 (including gap- GEL 660,000) | 0
1.2.1.23 | Deliver trainings to support farms and cooperatives | 1.2.1.23.1 | At least 400 farmers/cooperative members trained | Report of the Environmental Information and Education Center, LEPL | Environmental Information and Education Center, LEPL |  | 2027, IV | 60000 | 60000 | 31 11 01 |  |  |  | 15000 | 15000 | 15000 | 15000
1.2.1.24 | Align the legislation in agriculture and rural development with the EU legislation, including creating an action plan to ensure full compliance with the EU legislation on the Common Market Organization (CMO) | 1.2.1.24.1 | An action plan to ensure full compliance with the European legislation in the area of the Common Market Organization (CMO) developed | The developed action plan | The Ministry of Environmental Protection and Agriculture/ Agriculture and Rural Development Policy Department | UNDP | 2024, IV |  | Administrative costs
1.2.1.25 | Develop an action plan for creating an integrated administration and control system that aligns with EU legislation | 1.2.1.25.1 | An action plan for creating an integrated administration and control system that aligns with EU legislation developed | The developed action plan | Rural Development Agency, NCLE The Ministry of Environmental Protection and Agriculture/ Agriculture and Rural Development Policy Department | UNDP | 2024, IV |  | Administrative costs
1.2.1.26 | Initiate the development of the system similar to the Farm Accountancy Data Network (FADN) or Monitoring Farm Revenues and Performance | 1.2.1.26.1 | An action plan for the development of the Farm Accountancy Data Network (FADN) or a similar system for farm revenue and performance monitoring in place | The developed action plan | The Ministry of Environmental Protection and Agriculture/ Agriculture and Rural Development Policy Department | UNDP | 2024, IV |  | Administrative costs
1.2.1.27 | Develop a relevant action plan for establishing a nationwide land plot identification system | 1.2.1.27.1 | An action plan for establishing a nationwide land plot identification system developed | The developed action plan | Rural Development Agency, NCLE The National Agency for Sustainable Land Management and Land Use Monitoring, LEPL The Ministry of Environmental Protection and Agriculture/ Agriculture and Rural Development Policy Department | UNDP | 2024, IV |  | Administrative costs
OBJECTIVE 1.3: |  | To support the integration of farmers/entrepreneurs into the market
OUTCOME INDICATOR 1.3.1: |  | Number of beneficiaries who introduced/certified international quality/production systems/standards or quality schemes |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Rural Development Agency, NCLE website
|  |  |  | Value | 184 | 244 |  | 304
Risk: |  | Low activeness of potential beneficiaries
Activity |  | Output Indicator |  | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
1.3.1.1 | Co-financing farmers for the introduction of international food production standards, certification and branding | 1.3.1.1.1 | 80 beneficiaries have implemented international food safety standards and 40 beneficiaries have their company/products branded; | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 7000000 | 7000000 | 31 05 08 |  |  |  | 1000000 | 2000000 | 2000000 | 2000000
1.3.1.2 | Organize exhibition-tasting activities to promote Georgian agri-food products | 1.3.1.2.1 | 38 exhibitions and tasting events held worldwide (including in Georgia) | Annual report of he Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 12000000 | 12000000 | 31 05 11 |  |  |  | 3000000 | 3000000 | 3000000 | 3000000
1.3.1.3 | Development and supporting quality schemes | 1.3.1.3.1 | Specifications for 8 geographic indications will be developed/reviewed | Developed documents | The Ministry of Environmental Protection and Agriculture of Georgia / Food Policy Department |  | 2027,IV |  | Administrative costs
1.3.1.4 | Support the integration of agri-food product producers in the market | 1.3.1.4.1 | 20 agri-food producers will receive at least one quality mark and at least 8 agri- food product guides will be developed | Permits to use the quality mark issued; Guides Developed. | The Ministry of Environmental Protection and Agriculture of Georgia / The Marketing Council / Food Policy Department | National Food Agency, LEPL | 2027,IV |  | Administrative costs
1.3.1.5 | Conduct laboratory tests on samples of the wines available on the market | 1.3.1.5.1 | 3,800 alcoholic beverage samples will be drawn for laboratory testing of wine | Annual report of the National Wine Agency, LEPL | National Wine Agency, LEPL |  | 2027,IV | 2800000 | 2800000 | 31 03 02 |  |  |  | 700000 | 700000 | 700000 | 700000
1.3.1.6 | Facilitate promotion of Georgian wine products/organize events | 1.3.1.6.1 | In various countries around the world and domestically, 60 exhibitions/festivals of wine and alcoholic beverages, around 300 tasting events, about 40 wine tours for wine professional from various countries of the globe will be organized | Annual report of the National Wine Agency, LEPL | National Wine Agency, LEPL |  | 2027,IV | 72200000 | 72200000 | 31 03 03 |  |  |  | 16000000 | 17400000 | 19400000 | 19400000
1.3.1.7 | Complete and update the vineyard zones cadaster of Georgia | 1.3.1.7.1 | Ortho photos of 50,000 hectares will be updated in all regions of Georgia | Annual report of the National Wine Agency, LEPL | National Wine Agency, LEPL |  | 2027,IV | 2540000 | 2540000 | 31 03 04 |  |  |  | 500000 | 680000 | 680000 | 680000
1.3.1.8 | Developing the system of appellations of origin and geographical indications | 1.3.1.8.1 | Around 40 Georgian appellation of origin wines will be protected in various countries of the world; specification form for wine production will be developed for 5 new protected appellations of origin wines | Annual report of the National Wine Agency, LEPL | National Wine Agency, LEPL |  | 2027,IV | 400000 | 400000 | 31 03 06 |  |  |  | 100000 | 100000 | 100000 | 100000
1.3.1.9 | Promote the origin of Georgian vine |  | 30 local vine varieties and wild vine will be examined using ampelography and molecular genetics methods | Annual report of the National Wine Agency, LEPL | National Wine Agency, LEPL |  | 2027,IV | 700000 | 700000 | 31 03 07 |  |  |  | 100000 | 200000 | 200000 | 200000
OBJECTIVE 1.4: |  | To stimulate young farmers and entrepreneurs in rural areas
OUTCOME INDICATOR 1.4.1: |  | The number of young rural entrepreneurs funded in the frame of the program for supporting small and micro enterprises |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual report of Enterprise Georgia, LEPL
|  |  |  | Value | 518 | 900 |  | 1 318
Risk: |  | Reduced activity within the Program's framework
Activity |  | Output Indicator |  | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | დეფიციტი (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
1.4.1.1. | Grants provided to young entrepreneurs in rural areas through the Program for Supporting Small and Micro Entrepreneurship | 1.4.1.1.1 | Grants provided to 800 young (up to 30 years) entrepreneurs operating in rural areas | Annual report of Enterprise Georgia, LEPL | The Ministry of Economy and Sustainable Development of Georgia / Enterprise Georgia, LEPL |  | 2027,IV | 19200000 | 19200000 | 24 07 02 01 |  |  |  | 4800000 | 4800000 | 4800000 | 4800000
OBJECTIVE 1.5: |  | To increase access to infrastructure and services
OUTCOME INDICATOR 1.5.1: |  | Local roads constructed/rehabilitated |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual Reports of the Ministry of Regional Development and Infrastructure of Georgia
|  |  |  | Value | 544 km | 944 km |  | 1344 km
OUTCOME INDICATOR 1.5.2: |  | Kindergarten built/rehabilitated |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual Reports of the Ministry of Regional Development and Infrastructure of Georgia
|  |  |  | Value | 9 ea. | 144 ea. |  | 214 ea.
OUTCOME INDICATOR 1.5.3: |  | Sports, culture and recreational facilities built/rehabilitated |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual Reports of the Ministry of Regional Development and Infrastructure of Georgia
|  |  |  | Value | 26 ea. | 46 ea. |  | 66 ea.
OUTCOME INDICATOR 1.5.4: |  | Water supply and sewage systems and auxiliary structures built/rehabilitated |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual Reports of the Ministry of Regional Development and Infrastructure of Georgia
|  |  |  | Value | 235 km | 435 km |  | 585 km
Risk: |  | Insufficient funds; natural disasters.
Activity |  | Output Indicator |  | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
1.5.1.1 | Develop databases (registries) of farmers | 1.5.1.1.1 | 48,000 farmers/farms will be registered in the program for the registration of farms/farmers | Annual report of the Ministry of Environmental Protection and Agricultureს of Georgia | The Ministry of Environmental Protection and Agriculture Rural Development Agency, NCLE |  | 2027, IV | 1600000 | 1600000 | 31 05 07 |  |  |  | 400000 | 400000 | 400000 | 400000
1.5.1.2 | Construction of public schools | 1.5.1.2.1 | The construction of over 50 public schools completed | The State Budget Implementation Report | The Ministry of Education, Science and Youth of Georgia |  | 2027, IV | 435000000 | 435000000 | 32 07 01 |  |  |  | 130500000 | 179800000 | 120700000 | 4000000
1.5.1.3 | Complete rehabilitation of public schools | 1.5.1.3.1 | Reconstruction/rehabilitation of over 90 public schools completed | The State Budget Implementation Report | The Ministry of Education, Science and Youth of Georgia |  | 2027, IV | 666150000 | 666150000 | 32 07 01 |  |  |  | 122600000 | 343550000 | 200000000 | 0
1.5.1.4 | Equipping public schools with supplies | 1.5.1.4.1 | Around 500 additional public schools are equipped with office furniture, classroom desks and chairs, classroom boards | The State Budget Implementation Report | The Ministry of Education, Science and Youth of Georgia |  | 2027, IV | 94075000 | 94075000 | 32 07 01 |  |  |  | 23540500 | 23511500 | 23511500 | 23511500
1.5.1.5 | Road cover paved/rehabilitated on the sections of local roads | 1.5.1.5.1 | 800 km road pavement will be constructed/rehabilitated | Reports of the Ministry of Regional Development and Infrastructure of Georgia | The Ministry of Regional Development and Infrastructure of Georgia | Municipalities; Roads Department of Georgia; Municipal Development Fund of Georgia, LEPL; | 2027, IV | 300000000 | 300000000 | 25 02 / 25 03 / 55 07 |  | - | 0 | 75000000 | 75000000 | 75000000 | 75000000
1.5.1.6 | Construction/rehabilitation of kindergartens | 1.5.1.6.1 | 205 kindergartens will be built/rehabilitated | Reports of the Ministry of Regional Development and Infrastructure of Georgia | The Ministry of Regional Development and Infrastructure of Georgia | Municipal Development Fund of Georgia, LEPL; Municipalities | 2027, IV | 420000000 | 420000000 | 25 07 02 / 5507 |  | - | 0 | 210000000 | 70000000 | 70000000 | 70000000
1.5.1.7 | Construction/rehabilitation of sports, culture and recreational infrastructure | 1.5.1.7.1 | 40 sports, culture and recreational facilities will be built/rehabilitated | Reports of the Ministry of Regional Development and Infrastructure of Georgia | The Ministry of Regional Development and Infrastructure of Georgia | Municipal Development Fund of Georgia, LEPL; Municipalities | 2027, IV | 12000000 | 12000000 | 55 07 / 25 03 |  | - | 0 | 3000000 | 3000000 | 3000000 | 3000000
1.5.1.8 | Construction/rehabilitation of water supply and sewage systems | 1.5.1.8.1 | 30 projects for the arrangement and construction of water supply and sewage network and auxiliary structures (boreholes, reservoirs, mains, treatment structure) implemented | Reports of the Ministry of Regional Development and Infrastructure of Georgia | The Ministry of Regional Development and Infrastructure of Georgia | United Water Supply Company of Georgia, LLC; Municipalities | 2027, IV | 85000000 | 85000000 | 25 04 06 / 25 03 / 55 07 |  | - | 0 | 25000000 | 25000000 | 25000000 | 10000000
OBJECTIVE 1.6: |  | To improve the irrigation and drainage systems
OUTCOME INDICATOR 1.6.1: |  | Area of available hydro ameliorated land |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | LDT "Georgian Amelioration" Report
|  |  |  | Value | 186.347 ha | 196,200 ha |  | 203,355 ha
Risk: |  | Force-majeure events, delays in the procurement procedure, delays in the timeframes of the construction process (implementation of works), other contingencies
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
1.6.1.1 | Rehabilitation of the amelioration systems | 1.6.1.1.1 | 16.0 thousand ha land to be moved into regularly irrigated areas; Improvement of the provisioning of water to irrigated lands 29.67 thousand ha; drying land areas 0.9 thousand ha; | Report of Georgian Amelioration, LLC | Georgian Amelioration, LLC | The Ministry of Environmental Protection and Agriculture of Georgia | 2027,IV | 202000000 | 202000000 | 31 06 01 |  |  |  | 37000000 | 55000000 | 55000000 | 55000000
1.6.1.2 | Improvement of irrigation in selected irrigation and drainage systems | 1.6.1.2.1 | Selected irrigation and drainage systems rehabilitated and/or modernized | Report of the Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture of Georgia | WB The World Bank | 2027,IV | 70620000 | 70620000 | 31 06 04 |  | WB The World Bank |  | 2000000 | 17520000 | 21900000 | 29200000
1.6.1.3 | Financial support to local farmers in selected irrigation and drainage systems | 1.6.1.3.1 | Co-financing based grants issued for selected irrigation and drainage systems | Report of the Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture of Georgia | WB The World Bank | 2027,IV | 13665400 | 13665400 | 31 06 04 |  | WB The World Bank |  | 2000000 | 2978400 | 3723000 | 4964000
1.6.1.4 | Prepare a feasibility study for Ilto irrigation water reservoir and the assessment of dam safety for 5 water reservoirs | 1.6.1.4.1 | Dam safety situation for 5 water reservoirs assessed and established (Narekvavi, Mtskheta-Mtianeti, Dusheti Municipality, Iakublo, Mtisdziri, Pantiani, Khorkhori- Kvemo kartli, Dmanisi Municipality) | Report of the Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture of Georgia | WB The World Bank | 2027,IV | 2684000 | 2684000 | 31 06 04 |  | WB The World Bank |  | 805200 | 1610400 | 268400 | 0
1.6.1.5 | Improvement of irrigation for Kvemo Samgori irrigation and drainage system | 1.6.1.5.1 | The left main channel and distribution networks of Kvemo Samgori rehabilitated and/or modernized | Report of the Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture of Georgia | ADB The Asian Development Bank | 2027,IV | 68756000 | 68756000 | 31 06 05 01 |  | ADB The Asian Development Bank |  | 500000 | 22752000 | 22752000 | 22752000
1.6.1.6 | Improvement of irrigation for Zemo Samgori irrigation and drainage system | 1.6.1.6.1 | Upper and lower main channels and distribution networks of Zemo Samgori rehabilitated and/or modernized | Report of the Ministry of Environmental Protection and Agriculture of Georgia | The Ministry of Environmental Protection and Agriculture of Georgia | EIB The European Investment Bank | 2027,IV | 44750000 | 44750000 | 31 06 05 02 |  | EIB The European investment Bank |  | 500000 | 8850000 | 17700000 | 17700000
OBJECTIVE 1.7: |  | To develop rural tourism and relevant tourism products
OUTCOME INDICATOR 1.7.1: |  | Improved new marked trails length (kilometers) |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual report of the Georgian National Tourism Administration, LEPL
|  |  |  | Value | 0 | 200 კმ |  | 300 კმ
Risk: |  | Certain Force-majeure event beyond our control that cannot be foreseen
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
1.7.1.1 | Development of rural touristic products | 1.7.1.1.1 | 8 touristic products created | Annual report of the National Tourism Administration of Georgia | The Ministry of Economy and Sustainable Development of Georgia / Georgian National Tourism Administration, LEPL |  | 2027,IV | 1400000 | 1400000 | 24 05 02 |  |  |  | 350000 | 350000 | 350000 | 350000
1.7.1.2 | Development of small-scale touristic infrastructure | 1.7.1.2.1 | 4 infrastructure projects created | Annual report of the National Tourism Administration of Georgia | The Ministry of Economy and Sustainable Development of Georgia / Georgian National Tourism Administration, LEPL |  | 2027,IV | 1600000 | 1600000 | 24 05 02 |  |  |  | 400000 | 400000 | 400000 | 400000
1.7.1.3 | Development of the skills of the private sector in touristic services (The retraining program) | 1.7.1.3.1 | 3,200 beneficiaries trained | Annual report of the National Tourism Administration of Georgia | The Ministry of Economy and Sustainable Development of Georgia / Georgian National Tourism Administration, LEPL |  | 2027,IV | 1200000 | 1200000 | 24 05 02 |  |  |  | 300000 | 300000 | 300000 | 300000
GOAL 2: |  | Sustainable usage of natural resources, retaining of the eco-system, adaptation to climate change |  |  |  |  | Link to SDGs: |  | 13; 15; 6
IMPACT Indicator 2.1: |  | Number of farmers and individuals employed in the agricultural sector who have raised their awareness in the adaptation of agriculture to climate change to ensure agricultural sustainability |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm | Final
|  |  |  | Year | 2023 | 2025 | 2027 |  | Annual report of the Ministry of Environmental Protection and Agriculture
|  |  |  | Value | 0 | 100 | 150
IMPACT Indicator 2.2: |  | Number of reports prepared about climate related risks to improve the integration of adaptation to climate change in the planning and management in the forestry sector |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm | Final
|  |  |  | Year | 2023 | 2025 | 2027 |  | Annual report of the Ministry of Environmental Protection and Agriculture
|  |  |  | Value | 0 | 2 | 3
OBJECTIVE 2.1. |  | To disseminate climate-smart and environmentally adapted agricultural practices and promotion of bio-organic production development
OUTCOME INDICATOR 2.1.1: |  | Farmers' awareness raised about nitrate vulnerable zones and good agricultural practices, with the goal of adaptation to climate change in the agricultural sector |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual report of the Ministry of Environmental Protection and Agriculture
|  |  |  | Value | 0 | 100 ფერმერი |  | 150 ფერმერი
Risk: |  | Insufficient human recourses; inadequate support from stakeholders;
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
2.1.1.1 | Establish good agricultural practices for nitrate vulnerable zones | 2.1.1.1.1 | A guide about good agricultural practices for nitrate vulnerable zone developed | Report of a respective donor project | The Ministry of Environmental Protection and Agriculture / The Department of Environment and Climate Change |  | 2024,IV | 300000 |  |  | 300000 | EU |  | 300000
2.1.1.2 | Determine and support capacity for the adaptation of the agricultural sector to climate change | 2.1.1.2.1 | Developed analysis about existing capacity for adaptation of the agricultural sector to climate change Action plan for the adaptation of the agricultural sector to climate change developed | Developed national adaptation plan | The Ministry of Environmental Protection and Agriculture/ The Department of Environment and Climate Change |  | 2027,IV | 1000000 |  |  | 1000000 | The Global Climate Fund (GCF) |  | 250000 | 250000 | 250000 | 250000
2.1.1.3 | Raise farmers' awareness about nitrate vulnerable zones and good agricultural practices | 2.1.1.3.1 | At least 100 farmers have raised their awareness about nitrate vulnerable zones and good agricultural practices | Report of the relevant donor project | The Ministry of Environmental Protection and Agriculture / Department of Environment and Climate Change |  | 2024, IV |  | Administrative costs
2.1.1.4 | Implement awareness-raising activities about climate-smart agricultural practice, including training courses | 2.1.1.4.1 | At least four events implemented | Report of the Environmental Information and Education Center, LEPL | Environmental Information and Education Center, LEPL |  | 2027, IV | 16000 | 16000 | 31 11 01 |  |  |  | 4000 | 4000 | 4000 | 4000
OBJECTIVE 2.2: |  | To support the development of eco tourism
OUTCOME INDICATOR 2.2.1: |  | The number of protected areas with arranged infrastructure for the development of eco tourism |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Report of the Agency for Protected Areas, LEPL
|  |  |  | Value | Infrastructure developed in 14 sites falling under the management of 11 administrations of the protected areas | Infrastructure developed in 23 sites falling under the management of 17 Administrations of the protected areas |  | Infrastructure developed in 25 sites falling under the management of 20 administrations of the protected areas
Risk: |  | Situation due to the Pandemic; lower priority in the process of budgeting
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
2.2.1.1 | Improvement of infrastructure on touristic routes in the protected areas | 2.2.1.1.1 | At least eight (8) (two each year) eco-tourism infrastructure arranged/improved along the touristic routes in the protected areas | Official data from the Agency of Protected Areas, LEPL | The Ministry of Environmental Protection and Agriculture of Georgia / The Agency of Protected Areas, LEPL |  | 2027, IV | 4000000 | 4000000 | 31 08 03 |  |  |  | 1000000 | 1000000 | 1000000 | 1000000
2.2.1.2 | Equip the protected areas with infrastructure | 2.2.1.2.1 | 12 units of security infrastructure (rangers' house, blockage, etc.) arranged/rehabilitated in the protected areas. 200 (50 per year) anti-incendiary equipment purchased. | Official data from the Agency of Protected Areas, LEPL | The Ministry of Environmental Protection and Agriculture of Georgia / The Agency of Protected Areas, LEPL |  | 2027, IV | 200000 | 200000 | 31 08 02 |  |  |  | 50000 | 50000 | 50000 | 50000
OBJECTIVE 2.3: |  | Sustainable usage of forest resources
OUTCOME INDICATOR 2.3.1 |  | The volume of sustainably sourced timber |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual Report of the National Forestry Agency, LEPL
|  |  |  | Value | 100 000 m3 | 170 000 m3 |  | 190 000 m3
Risk: |  | Reduction in the state budget and/or other revenues, insufficient financing, low awareness among the population
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
2.3.1.1 | The management of timber resources | 2.3.1.1.1 | Availability of the allocated 1,800,000 m3 timber resources | Annual report of the National Forestry Agency, LEPL | National Forestry Agency, LEPL |  | 2027, IV | 160970000 | 61550000 | 31 09 03 | 99420000 | The National Forestry Agency, LEPL (Own funds) |  | 36990000 | 39685000 | 39985000 | 44310000
2.3.1.2 | Maintenance and restoration of the forest | 2.3.1.2.1 | Forests will be developed/restored on additional 10,796 ha area | Annual report of the National Forestry Agency, LEPL | National Forestry Agency, LEPL |  | 2027, IV | 13700000 | 2800000 | 31 09 02 | 10900000 | The National Forestry Agency, LEPL (Own funds) |  | 6250000 | 2450000 | 2450000 | 2550000
2.3.1.3 | Implement forest inventory | 2.3.1.3.1 | Draft forest management plans will be additionally developed for 8 forest sections (620,000 ha) | Annual report of the National Forestry Agency, LEPL | National Forestry Agency, LEPL |  | 2027,IV | 3400000 | 1000000 | 31 09 04 | 2400000 | The National Forestry Agency, LEPL (Own funds) |  | 850000 | 850000 | 850000 | 850000
OBJECTIVE 2.4: |  | To support the implementation of energy-efficient and renewable energy technologies and practices
OUTCOME iNDICATOR:2.4.1 |  | The number of retrained skilled employees who will contribute to the implementation of energy efficient and renewable energy technologies and practice |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2024 |  | 2024 | wwww.moesd.gov.ge
|  |  |  | Value | 34 | 73 |  | 73
Risk: |  | Low participation rate of installation workers from regions in the program; complexity of drafting of sub-legal acts involving active discussions with stakeholders that may result in prolonging the timeframes
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
2.4.1.1 | Draft sub-legal acts on the production of bio fuel | 2.4.1.1.1 | Sub-legal act drafted | www.matsne.gov.ge | The Ministry of Economy and Sustainable Development |  | 2024 IV |  | Administrative costs
2.4.1.2 | Retrain the installation workers for the equipment for the production of energy from renewable sources | 2.4.1.2.1 | The number of trained installation workers | www.moesd.gov.ge | The Ministry of Economy and Sustainable Development | National Center for Educational Quality Enhancement, educational institutions | 2024 IV |  | Administrative costs
2.4.1.3 | Approve the training programs in accordance with the Law of Georgian on Energy Efficiency | 2.4.1.3.1 | 4 training programs developed | www.matsne.gov.ge | The Ministry of Economy and Sustainable Development | National Center for Educational Quality Enhancement, Skills Agency | 2024 IV |  | Administrative costs
OBJECTIVE 2.5: |  | To maintain agro-biodiversity
OUTCOME INDICATOR : 2.5.1 |  | The protected amount of genetic resources of local agricultural flora and fauna researched by the Scientific-Research Center of Agriculture |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual reports of the Scientific-Research Center of Agriculture, LEPL
|  |  |  | Value | 0 | 7040 |  | 7550
Risk: |  | Lack of funding; funds not allocated for upgrading the genetic bank infrastructure
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
2.5.1.1 | Identifying, restoring and improving local agricultural animal species and support their population growth | 2.5.1.1.1 | 6,400 heads of traceable individuals and 150 heads of breeding animals | Annual reports of the Scientific-Research Center of Agriculture | The Ministry of Environmental Protection and Agriculture / Scientific-Research Center of Agriculture, LEPL |  | 2027, IV | 2600000 | 2600000 | 31 04 02 |  |  |  | 800000 | 600000 | 600000 | 600000
2.5.1.2 | Identify and maintain annual and perennial crops, support expanding their prevalence | 2.5.1.2.1 | 1,000 varieties of protected perennial crops introduced in the collection and 1,000 specimens will be stored in the genetic bank | Annual reports of the Scientific-Research Center of Agriculture | The Ministry of Environmental Protection and Agriculture / Scientific-Research Center of Agriculture, LEPL |  | 2027, IV | 7860000 | 7860000 | 31 04 03 |  |  |  | 1770000 | 2030000 | 2030000 | 2030000
2.5.1.3 | Further development of the certification scheme for seeds and planting stock | 2.5.1.3.1 | 9,200 tons of certified seed material and 802,000 units of certified planting stock | Annual reports of the Scientific-Research Center of Agriculture | The Ministry of Environmental Protection and Agriculture / Scientific-Research Center of Agriculture, LEPL
2.5.1.4 | Conduct trainings for farmers on hydroponic production of vegetable crops | 2.5.1.4.1 | 12 trainings delivered for farmers | Annual reports of the Scientific-Research Center of Agriculture | The Ministry of Environmental Protection and Agriculture / Scientific-Research Center of Agriculture, LEPL
GOAL 3: |  | Effective systems of food/feed safety, veterinary and plant protection |  |  |  |  | Link to SDGs: |  | 3;6
IMPACT Indicator 3.1. |  | Reduce noncompliances identified as a result of laboratory tests of samples of food and potable water in the course of state food safety control |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm | Final
|  |  |  | Year | 2023 | 2025 | 2027 |  | National Food Agency Report, LEPL
|  |  |  | Value | 13% | 12.2% | 10%
OBJECTIVE 3.1 |  | To approximate the sanitary and phytosanitary regulatory legislation of Georgia to the EU legislation
OUTCOME INDICATOR 3.1.1: |  | Georgia's legislation governing sanitary and phytosanitary fields is approximated to the EU legal act stipulated under XI-B Annex of the Association Agreement. |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | www.matsne.gov.ge
|  |  |  | Value | 136 | 153 |  | 200
Risk: |  | The number of legal acts may change, given the dynamic nature of legislative approximation, some acts may be abolished and/or several acts may be consolidated, which will automatically result in the change of the number of normative acts to be approximated. Given the specificity of the EU legislative framework, the assistance of international experts/organizations may become necessary in the process of the development of the normative framework, which may extend the lawmaking process. Due to the substance of various legal acts, consultations with business/stakeholders may become necessary, which may delay the process of the approval of the legal act.
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
3.1.1.1 | Approximation of Georgia's legislation governing sanitary and phytosanitary fields to the EU legal act stipulated under XI-B Annex of the Association Agreement | 3.1.1.1.1 | Georgia's legislation in food safety, veterinary and plant protection is approximated to about 60 EU legislative acts | Legislative Herald of Georgia www.matsne.gov.ge | The Ministry of Environmental Protection and Agriculture |  | 2027, IV |  | Administrative costs
OBJECTIVE 3.2 |  | To ensure that the products supplied to the local and export markets comply with sanitary and phytosanitary standards
OUTCOME INDICATOR 3.2.1: |  | The number of different procedures conducted for animal health |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Official data from the National Food Agency, LEPL
|  |  |  | Value | 5 634 000 | 9 552 000 |  | 13 245 965
OUTCOME INDICATOR 3.2.2: |  | The percentage share of inspected business operators who are compliant with the relevant food safety regulations |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Official data from the National Food Agency, LEPL
|  |  |  | Value | 21% | 23% |  | 26%
Risk: |  | Capacities of laboratories, specifically: methods for testing food for various indicators are not in place and the lack of relevant accreditation; lack of competent food safety specialists; identifying new disease in the country; change in the numbers of animals; climatic conditions.
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
3.2.1.1 | Exercise state food safety control | 3.2.1.1.1 | 35,200 planned inspections will be conducted, 21,200 food samples will be tested in labs, 30,200 documentary inspections will be conducted, 400 HACCP audits will be conducted in animal slaughter-houses. | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV | 32706100 | 32706100 | 31 02 02 |  |  |  | 3900000 | 4000000 | 4000000 | 20806100
3.2.2.2 | Protection of animal health and traceability | 3.2.2.2.1 | 14,008,400 procedures will be conducted for preventative vaccination (foot-and-mouth, anthrax, rabies, brucellosis, nodular dermatitis, sheep and goat pox) | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV | 87000000 | 87000000 | 31 02 03 |  |  |  | 21000000 | 18000000 | 24000000 | 24000000
|  | 3.2.2.2.2 | Field studies using the allergy method will be conducted for animal infectious diseases and tuberculosis: serological test of large cattle for brucellosis 2,700,000 enzootic leucosis large cattle serological test 2026 - 1,340,000; 2027 850,000; diagnostic laboratory tests 5,050,000 samples for tuberculosis field allergy method survey of around 1,940,000 samples | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV
|  | 3.2.2.2.3 | Each year, around 920,000 livestock will be treated against ectoparasites at veterinary surveillance points | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV
|  | 3.2.2.2.4 | Approximately 5,233,400 large cattle and small cattle will be identified and registered | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV
3.2.2.3 | Exercise veterinary control | 3.2.2.3.1 | Taking 485 samples of biological material (blood) of live animals and feed of food-producing animals, testing for 15 indicators and making 1,880 tests; testing about 188 samples to monitor the quality of veterinary preparations; to test for salmonellosis and enterobacteria, 25-25 samples will be drawing and tested from 1 enterprise of processed food for pets biannually (a total of 100 samples from 1 enterprise a year), and 5-5 samples biannually from 1 enterprise producing fish powder (a total of 80 samples from 4 enterprises a year). Moreover, during the year, for the potential recognition of new enterprises of fish powder or ad hoc inspection of a recognized enterprise and for the investigation of salmonellosis and enterobacteria, additionally 10 samples will be tested; annually scheduled inspection of up to 935 facilities subjected to veterinary control will be performed. | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV
3.2.2.4 | Plant protection and the attainment and maintenance of phytosanitary reliability | 3.2.2.4.1 | Up to 400,000 ha area will be treated against pests, specifically, caterpillars, while about 100,000 ha will be treated against American White Moth and other pests. As necessary, areas will be treated against vectors (mosquitos) | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV | 11000000 | 11000000 | 31 02 04 |  |  |  | 2750000 | 2750000 | 2750000 | 2750000
|  | 3.2.2.4.2 | 2,000 samples will be drawn and control will be performed in about 1,600 facilities to prevent and stop the realization of expired and falsified pesticides and agrochemicals | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV
|  | 3.2.2.4.3 | Up to 6,000 samples will be drawn and lab tested for the identification of plant quarantine organisms | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV
3.2.2.5 | Carry out activities for controlling stink bug | 3.2.2.5.1 | About 800,000 ha area will be treated in the frame of the activities for controlling stinkbug, up to 20,000 pheromone traps will be arranged for controlling the pest, and up to 400,000 pheromones on Attract and Destroy stations | Annual reports of the National Food Agency, LEPL | The Ministry of Environmental Protection and Agriculture LEPL National Food Agency |  | 2027, IV | 78853000 | 78853000 | 31 02 05 |  |  |  | 22000000 | 25000000 | 21330000 | 10523000
OBJECTIVE 3.3. |  | To develop laboratory capacities
OUTCOME INDICATOR: 3.3.1 |  | 60 methods and 40 parameters will be implemented and/or accredited in the laboratory in accordance with the international standard |  | Year | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual report of the State Laboratory of Agriculture of Georgia, LEPL
|  |  |  | Value | 44 new methods and 15 new parameters were implemented in the laboratory and successfully accredited in all three areas; | 40 new methods and 20 parameters will be implemented in the laboratory and/or accredited |  | 60 new methods and 40 new parameters will be implemented in the laboratory
Risk: |  | Low activity level of customers, procedural delay in the supply of reference and other materials
# | Activity | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
3.3.1.1 | Implementation of new laboratory diagnostic methods and/or accreditation | 3.3.1.1.1 | 60 methods will be implemented and/or accredited in line with international standards | Annual report of the State Laboratory of Agriculture of Georgia, LEPL | The Ministry of Environmental Protection and Agriculture / State Laboratory of Agriculture of Georgia, LEPL |  | 2027,IV | 3424000 | 1012000 | 31 14 | 2412000 | State Laboratory of Agriculture (Own funds) |  | 856000 | 856000 | 856000 | 856000
3.3.1.2 | Implementation and/or accreditation of new parameters of laboratory diagnostics | 3.3.1.2.1 | 40 research parameters will be implemented and/or accredited in line with international standards | Annual report of the State Laboratory of Agriculture of Georgia, LEPL | The Ministry of Environmental Protection and Agriculture / State Laboratory of Agriculture of Georgia, LEPL
3.3.1.3 | Implementation of the innovative Laboratory Information Management System (LIMS) in the laboratory network | 3.3.1.3.1 | The innovative Laboratory Information Management System (LIMS) is implemented within the laboratory | Annual report of the State Laboratory of Agriculture of Georgia, LEPL | The Ministry of Environmental Protection and Agriculture / State Laboratory of Agriculture of Georgia, LEPL |  | 2027,IV | 2000000 |  | 31 14 | 2000000 |  |  | 1000000 | 1000000
OBJECTIVE 3.4 |  | Quality assurance of agricultural inputs
OUTCOME INDICATOR : 3.4.1 |  | The share of qualified nurseries compliant with international requirements and standards within the nurseries inspected by the Scientific-Research Center of Agriculture |  |  | Baseline | Target |  |  | Sources of Verification
[6 empty] | Midterm |  | Final
|  |  |  | Year | 2023 | 2025 |  | 2027 | Annual Reports of the Scientific-Research Center of Agriculture, LEPL
|  |  |  | Value | 62% | 71% |  | 75%
Risk: |  | Lack of funding; outflow of skilled workforce
# | Su | # | Output Indicator | Sources of Verification | Responsible Agency | Partner Agency | Deadline | Budget (₾) | Source of financing |  |  |  |  | Annual Budget Allocation
[9 empty] | State Budget |  | Other |  | Gap (₾) | 2024 | 2025 | 2026 | 2027
[9 empty] | Amount (₾) | Code | Amount (₾) | Organization |  | Amount (₾) | Amount (₾) | Amount (₾) | Amount (₾)
3.4.1.1 | Survey the land fund of Georgia | 3.4.1.1.1 | 80,000 ha of soils will be surveyed and 20 digital maps will be created | Annual reports of the Scientific-Research Center of Agriculture | The Ministry of Environmental Protection and Agriculture / Scientific-Research Center of Agriculture, LEPL |  | 2027,IV | 400000 | 400000 | 31 04 05 |  |  |  | 100000 | 100000 | 100000 | 100000
3.4.1.2 | Implement scientific research of the methods for the storage and processing of agricultural products | 3.4.1.2.1 | 12 recommendations will be issued for the storage and processing of fruits and vegetables, 10 technological guidelines will be developed | Annual reports of the Scientific-Research Center of Agriculture | The Ministry of Environmental Protection and Agriculture / Scientific-Research Center of Agriculture, LEPL |  | 2027,IV | 200000 | 200000 | 31 04 04 |  |  |  | 50000 | 50000 | 50000 | 50000